## Initiatives
Initiative ID | Initiative Name | Function | Status | Priority | Readiness | Estimated Cost (USD) | Benefit Range (USD) | Owner | Dependencies | Risks | Target Date | KPI Baseline | Pain Point
FT-001 | Close Process Automation | Record to Report | In Progress | High | Medium | 850000 | 1.2M - 1.8M | Sarah Chen | FT-004 | Vendor delivery delay | 2026-03-31 | Close cycle 8 days | Manual close steps
FT-002 | FP&A Planning Platform | FP&A | Planning | High | Low | 1200000 | 2.0M - 3.5M | Michael Torres | FT-006 | Data quality in source systems | 2026-06-30 | Planning cycle 15 days | Spreadsheet-driven planning
FT-003 | Intercompany Hub | Controllership | In Progress | High | Medium | 620000 |  | Lisa Park | FT-001 | Cross-border regulatory change | 2026-04-15 | IC mismatch rate 2.1% | Manual IC reconciliation
FT-004 | Accounts Payable Workflow | GBS | In Progress | High | High | 430000 | 0.8M - 1.1M | David Okonkwo |  | Change resistance | 2026-02-28 | Touchless rate 42% | Paper-based approvals
FT-005 | Management Reporting Hub | FP&A | Not Started | Medium | Low | 390000 | 0.5M - 0.9M |  | FT-002 | Unclear report ownership | 2026-09-30 |  | Fragmented reporting packs
FT-006 | Data Governance Framework | Finance IT | In Progress | Medium | Medium | 275000 | Not quantified | Priya Nair | FT-002 | Limited data steward capacity | 2026-05-31 | Master data accuracy 88% | Inconsistent chart of accounts
FT-007 | Treasury Workbench | Treasury | Planning | Low | Low | 510000 | 0.4M - 0.7M | James Walsh |  | Bank API availability | 2026-11-30 | Cash forecast accuracy 78% | Manual cash forecasting
FT-008 | Expense Policy Analytics | GBS | Complete | Low | High | 180000 | 0.2M - 0.3M | Emma Brooks |  |  | 2025-12-15 | Policy compliance 91% | Limited spend visibility

## KPI Summary
KPI | Baseline Value | Target Value | Notes
Finance close cycle (days) | 8 | 5 | Source: initiative FT-001
Planning cycle (days) | 15 | 7 | Source: initiative FT-002
Touchless AP rate (%) | 42 | 75 | Source: initiative FT-004
Master data accuracy (%) | 88 | 95 | Source: initiative FT-006