## RAID Register
ID | Type | Project | Description | Owner | Status | Date Raised | Target Date
R-01 | Risk | Project Alpha | Vendor payroll patch may delay cutover | John Smith | Open | 2026-08-01 | 2026-10-15
R-02 | Risk | Project Gamma | Data migration dependency on Alpha | Carlos Mendez | Open | 2026-07-20 | 2026-11-01
I-01 | Issue | Project Alpha | Payroll interface defect in test environment | John Smith | Open | 2026-09-05 | 2026-09-30
I-02 | Issue | Project Beta | Legacy SSO certificate expiring | Aisha Rahman | Closed | 2026-08-12 | 2026-09-01
A-01 | Assumption | Program | Vendor delivers patch by 30 September 2026 | Robert Singh | Active | 2026-08-01
D-01 | Dependency | Project Gamma | Requires Alpha data migration completion | Carlos Mendez | Open | 2026-06-01 | 2026-11-30
D-02 | Dependency | Project Beta | Requires network firewall rule approval | Aisha Rahman | Open | 2026-07-15 | 2026-10-01
D-03 | Dependency | Project Alpha | Requires HR policy sign-off before payroll go-live | John Smith | Open | 2026-05-10 | 2026-10-20
D-04 | Dependency | Program | Shared test environment availability | Robert Singh | Open | 2026-04-01 | 2026-09-30