## Action Register
Action ID | Action | Owner | Due Date | Status | Project / Workstream
ACT-001 | Submit vendor patch impact assessment | John Smith | 2026-09-05 | Overdue | Project Alpha
ACT-002 | Circulate updated cutover plan | Robert Singh | 2026-09-26 | Open | Program
ACT-003 | Complete firewall rule approval | Aisha Rahman | 2026-09-10 | Overdue | Project Beta
ACT-004 | Confirm HR policy sign-off | John Smith | 2026-09-15 | Overdue | Project Alpha
ACT-005 | Finalize Gamma migration prerequisites | Carlos Mendez | 2026-10-05 | Open | Project Gamma
ACT-006 | Publish weekly status dashboard | Robert Singh | 2026-09-22 | Open | Program