## Decision Register
Decision ID | Decision | Status | Project | Required By | Decision Maker | Notes
DEC-001 | Approve additional testing window for Alpha payroll interface | Made | Project Alpha | 2026-09-12 | Steering Committee | Recorded in 12 Sep minutes
DEC-002 | Approve revised Project Alpha go-live date | Required | Project Alpha | 2026-09-26 | Steering Committee | Conflict between status update and minutes
DEC-003 | Confirm Beta UAT entry criteria met | Made | Project Beta | 2026-09-12 | Steering Committee
DEC-004 | Approve Gamma acceleration funding | Required | Project Gamma | 2026-10-15 | Steering Committee | Deferred at last meeting